## To Do List
Project To Do List
To be completed by | Overall Progress |  | Deadline | Days left | Highlight Activities
Andres Gomez | 21.94% |  | 2026-07-11 | 22 days left | This Week [15 Jun - 21 Jun]
Automated Rate Confirmation Parser and Analytics Platform
Activity | Due By | Budget | Done | Progress | Notes
Planning | 2026-06-17 | 0 | YES | 100%
Manual Assisted Parser | 2026-07-01 | 0 |  | 31.67%
Dispatch Automation | 2026-07-07 | 0 |  | 0%
Expense Tracking | 2026-07-11 | 0 |  | 0%
Analytics Dashboard | 2026-07-14 | 0 |  | 0%
Smarter Extraction | 2026-07-25 | 0 |  | 0%
Formulas:
Days left = [Deadline]-TODAY() & " days left"

## MAP Checklist
Project To Do List
To be completed by: |  |  | Deadline: | Days left: | Highlight Activities
Andres Gomez |  |  | 2026-07-01 | 12 days left | This Month [1 - 30, Jun]
Manual Assisted Parser
Activity | Due By | Budget | Done | Progress | Notes
PDF Upload | 2026-06-20 | 0 |  | 95% | Streamlit App; Supabase DB
Text Extraction | 2026-06-18 | 0 |  | 95%
LLM/regex parsing into structured fields | 2026-06-25 | 0 |  | 0%
Editable Form | 2026-06-26 | 0 |  | 0%
Save to database | 2026-06-30 | 0 |  | 0%
Copyable Driver Message | 2026-07-01 | 0 |  | 0%
Formulas:
Days left: = [Deadline:]-TODAY() & " days left"

## Dispatch Automation
Project To Do List
To be completed by: |  |  | Deadline: | Days left: | Highlight Activities
Andres Gomez |  |  | 2026-07-07 | 18 days left | This Week [15 Jun - 21 Jun]
Dispatch Automation
Activity | Due By | Budget | Done | Progress | Notes
Driver Table | 2026-07-04 | 0 |  | 0%
Truck Table | 2026-07-04 | 0 |  | 0%
Driver Email Selection | 2026-07-02 | 0 |  | 0%
Email Template | 2026-07-01 | 0 |  | 0%
Send Email Button | 2026-07-05 | 0 |  | 0%
Sent-Message Log | 2026-07-07 | 0 |  | 0%
Formulas:
Days left: = [Deadline:]-TODAY() & " days left"

## Expense Tracking
Project To Do List
To be completed by: |  |  | Deadline: | Days left: | Highlight Activities
Andres Gomez |  |  | 2026-07-11 | 22 days left | This Week [15 Jun - 21 Jun]
Expense Tracking
Activity | Due By | Budget | Done | Progress | Notes
Diesel Input | 2026-07-08 | 0 |  | 0%
Maintenance Input | 2026-07-08 | 0 |  | 0%
Tolls/lumpers | 2026-07-09 | 0 |  | 0%
Reciepts Upload | 2026-07-09 | 0 |  | 0%
Associate expenses with truck and/or load | 2026-07-11 | 0 |  | 0%
Formulas:
Days left: = [Deadline:]-TODAY() & " days left"

## Analytics Dashboard
Project To Do List
To be completed by: |  |  | Deadline: | Days left: | Highlight Activities
Andres Gomez |  |  | 2026-07-14 | 25 days left | This Week [15 Jun - 21 Jun]
Analytics Dashboard
Activity | Due By | Budget | Done | Progress | Notes
Revenue By Truck | 2026-07-12 | 0 |  | 0%
Rate per mile | 2026-07-12 | 0 |  | 0%
Fuel cost per mule | 2026-07-13 | 0 |  | 0%
Gross margin by load | 2026-07-13 | 0 |  | 0%
Broker performance | 2026-07-14 | 0 |  | 0%
Maintenance by Truck | 2026-07-14 | 0 |  | 0%
Formulas:
Days left: = [Deadline:]-TODAY() & " days left"

## Smarter Extraction
Project To Do List
To be completed by: |  |  | Deadline: | Days left: | Highlight Activities
Andres Gomez |  |  | 2026-07-25 | 36 days left | This Week [15 Jun - 21 Jun]
Smarter Extraction
Activity | Due By | Budget | Done | Progress | Notes
broker-specific parsing rules | 2026-07-16 | 0 |  | 0%
confidence scores | 2026-07-19 | 0 |  | 0%
flagged missing fields | 2026-07-21 | 0 |  | 0%
duplicate load detection | 2026-07-23 | 0 |  | 0%
OCR/scanned PDF support | 2026-07-25 | 0 |  | 0% | Not important
Formulas:
Days left: = [Deadline:]-TODAY() & " days left"

## Settings & Calculations
Highlight Settings
The tables below store settings and calculations for the Highlight Activities drop down list. Any changes could result in errors or loss of functionality.
No Highlight |  |  | No Highlight
Interval: | Start: | End: | Due:
This Week | 2026-06-15 | 2026-06-21 | This Week [15 Jun - 21 Jun]
This Month | 2026-06-01 | 2026-06-30 | This Month [1 - 30, Jun]
This Quarter | 2026-03-01 | 2026-06-30 | This Quarter [1 Mar - 30 Jun]
This Year | 2026-01-01 | 2026-12-31 | This Year [2026]
Interval: |  |  | Interval:
Last Week | 2026-06-08 | 2026-06-14 | Last Week [8 Jun - 14 Jun]
Last Month | 2026-05-01 | 2026-05-31 | Last Month [1 - 31, May]
Last Quarter | 2025-12-01 | 2026-02-28 | Last Quarter [1 Dec - 28 Feb]
Last Year | 2025-01-01 | 2025-12-31 | Last Year
Selected Highlight: | 3 | This Week [15 Jun - 21 Jun] | TRUE
Highlight Start | 2026-06-15
Highlight End | 2026-06-21
Formulas:
Start: = IFERROR(IF([Start:, row above]=1,"",IF([Due:, row above],INDEX(C5:C15,C16),"")),"")
End: = [Start:]+6
End: = EDATE([Start:],1)-1